## Delivery
Delivery Phase Budget - Jane Pit Restoration Project
Delivery Phase Capital Costs
Cost heading | Description | Cost | VAT | Total | Revised | Notes
Purchase price of items or property |  | 0
Repair and conservation work | Repair and restoration work to Jane Pit | 129000 |  | 129000 | 176295 | See tab for breakdown
New building work |  | 0
Other Capital work | Landscaping | 32300 |  | 32300 | 20706 | See Landscaping plan for breakdown
Digital outputs |  | 0
Equipment and materials (capital) |  | 0
Other costs (capital) |  | 0
Professional fees relating to any of the above (capital) | CDM consultation and principal designer costs | 2700 |  | 2700 | 32630 | See tab for breakdown
TOTAL CAPITAL COSTS |  | 164000 |  | 164000 | 229631
Delivery Phase Activity Costs
Cost heading | Description | Cost | VAT | Total | Revised | Notes
New staff costs
Training for staff
Paid training placements
Training for volunteers | Delivered in archaeological fees
Travel for staff
Travel and expenses for volunteers
Equipment and materials (activity) | Site facilities, security, fencing, wet weather contingency | 8200 |  | 8200 | 6200 | Welfare facilities £300 Site security (2 people 12 hours a night for 10 days) £3100 Fencing £260 Wet weather contingency £2540
Other costs (activity) | Refreshments | 300 |  | 300 | 0 | Refreshments are included in all invididual event costs
Professional fees relating to any of the above (activity) | Design and archaeological delivery, community engagement workshops | 19800 |  | 19800 | 32765 | Excavation Jane Pit £18,000 Virtual Museum (3D digital aerial survey) £1500 Excavation reporting, analysis, archiving £9,265 Mining the archives £2,000 Tales of the pit £2,000
TOTAL ACTIVITY COSTS |  | 28300 |  | 28300 | 38965
Delivery Phase Other Costs
Cost heading | Description | Cost | VAT | Total | Revised | Notes
Recruitment
Publicity and promotion | Leaflets/posters/banners | 200 |  | 200 | 200
Evaluation |  |  |  |  | 2000 | Focus of community engagement officer has shifted more towards evaluation as Dig Ventures take on a lot of the original proposed community engagement. The CEO will provide support and contacts
Other costs | Launch event, other events, photography, interpretation | 30800 |  | 30800 | 6710 | Launch event £1800 Landscape drawing session £200 Victorian / mine storytelling £20 The science of mining £20 Coffee and chat £100 Photography £200 Inerpretation panels £4370 (see tab for breakdown) The lightining element of the project has been removed hence the reduction in cost for this budget line
Full cost recovery
Contingency | Contingency also built into consolidation works breakdown | 29100 |  | 29100 | 14300 | Contingency has been built into the consolidation works which is why this figure has reduced.
Inflation | Total costs of capital and activity costs with 4.75% inflation over 4 years | 40200 |  | 40200 | 12758.31 | The original figure was incorrect and was not 5% inflation of the originally submitted costs during stage 1
Increased management and maintenance costs (max. 5 years) | Grounds and building maintenance | 34400 |  | 34400 | 34400 | Long term maintenance over 5 years
Non-cash contributions
Volunteer time
TOTAL OTHER COSTS |  | 134700 |  | 134700 | 70368.31
Delivery Phase Income
Cost heading | Description | Cost | VAT | Total | Revised | Notes
Local authority
Other public sector
Central government
European Union
Private donation - Individual
Private donation - Trusts/Charities/Foundations
Private donation - corporate
Commercial business
Own reserves | Community Engagement Consultation. Contribution towards landscaping | 3300 |  | 3300 | 7600 | Community Engagement Consultant - £2000 on evaluation WTC contribution towards landscaping - £5600
Other fundraising |  |  |  |  | 7000 | We are looking to secure some external funding - and have sent a number of sponsorship requests to local companies and submitted for grants. See fundraising plan for more information. £250 already secured from Dobies
Loan/Finance
Increased management and maintenance costs (max. 5 years) | Town Council budget | 34400 |  | 34400 | 34400 | Long term maintenance over 5 years
Non-cash contributions
Volunteer time
HLF Grant request |  | 289300 |  | 289300 | 289664
TOTAL INCOME |  | 327000 |  | 327000 | 338664
TOTALS | Original submission at stage 1 | Revised
TOTAL CAPITAL COSTS | 164000 | 229631
TOTAL ACTIVITY COSTS | 28300 | 38965
TOTAL OTHER COSTS | 134700 | 70368.31
TOTAL INCOME | 327000 | 338664
Delivery Phase - Financial Summary | Phase 1 submitted | Phase 2 | Difference
Total delivery costs | 327000 | 338964.31 | -11964.31
Total delivery income | 37700 | 49000 | 11300
HLF delivery grant request | 289300 | 289964.31 | -664.31
HLF delivery grant % |  | 0.86

## Breakdown of consolidation work
Project: | Jane Pit
Location: | Workington
Client: | Workington Town Council
Job Ref: | 1485
Date: | 18.02.19
| Consolidation Works |  | ASKIN and LITTLE |  |  |  | MAYSLAND |  |  |  | MGM
REF | DESCRIPTION | UNIT | QUANT | RATE | COST (£) | UNIT | QUANT | RATE | COST (£) | UNIT | QUANT | RATE | COST (£)
General & CDM
1.1 | Allow for acting as Principal Contractor (and if required with control of other contractors on site). Allow for all necessary information, risk assessments, statements etc. that may be necessary for the implementation of the CDM Regulations. | item |  |  | 31460 | item |  |  | 31568 | item |  |  | inc
1.2 | Allow for the fencing of the areas of work within the mine site and for setting up an external compound, safeguarding of work areas and provision of welfare facilities as required under CDM Regulations. | item |  |  | 0 | item |  |  | 3363.92 | item |  |  | 12200
1.3 | Provide access scaffold, all necessary artificial lighting and temporary electrical installations to carry out the work | item |  |  | 0 | item |  |  | included | item |  |  | 24000
1.4 | Allow for initial visits, measuring up and approvals and clarifications on Spec items and drawings. | item |  |  | 600 | item |  |  | 768.96 | item |  |  | 250
|  |  |  | Sub Total | 32060 |  |  | Sub Total | 35700.88 |  |  | Sub Total | 36450
Works to Freestanding Chimney
3.6 | Repair two external stone/brick arches. New bricks/stonework to be inserted to re-form the arches. Work to be constructed in NHL5.0. | item |  |  | 1000 | item |  |  | 4900.8 | item |  |  | 1275
3.9 | Provide for the design, erection, maintenance and removal of scaffold, to provide access up to 10m from the base of the chimney. | item |  |  | 8000 | item |  |  | 12590.6 | item |  |  | 7200
3.1 | Allow for installing 30m of Helifix 6mm stainless steel bed reinforcement into existing masonry and repointing as necessary. | m | 30 | 46 | 1380 | m | 30 |  | 2101.8 | m | 30 | 0 | 1350
|  |  |  | Sub Total | 10380 |  |  | Sub Total | 19593.2 |  |  | Sub Total | 9825
Works to Engine House
4.1 | Allow for inspection of attached chimney, from top down inside and out, by steeplejacks. Include for all temporary access requirements. | item |  |  | 4000 | item |  |  | 3080 | item |  |  | 1500
4.2 | Provide for the design, erection, maintenance and removal of scaffold, to provide access to the top of the attached chimney, and the internal and external faces of the walls. | item |  |  | 16000 | item |  |  | 28925.6 | item |  |  | 23000
4.3 | Take down the top 3 courses of the chimney and consolidate the top. | item |  |  | 1500 | item |  |  | 768.96 | item |  |  | 2040
4.4 | Remove all vegetation growing from the structure | item |  |  | 780 | item |  |  | 576.72 | item |  |  | 270
4.5 | Allow for sampling and testing of existing internal and external stonework, to inform specification of new stone | item |  |  | 600 | item |  |  | 384.48 | item |  |  | 300
4.6 | Allow for sampling and testing of existing internal and external mortar, to inform specification of new mortar |  |  |  | 600 |  |  |  | 384.48 |  |  |  | 300
4.7 | Provide new internal leaf of masonry, where internal stonework is missing. Allow for consolidation and/or removal of loose masonry. Construction to be in matching stone with NHL 2.0 lime mortar. Internal leaf approx. 300mm +/- 100mm | m2 | 20 | 460 | 9200 | m2 | 20 |  | 17579.2 | m2 | 20 | 0 | 4200
4.8 | Install new internal stone sills | No. | 2 | 400 | 800 | No. | 2 |  | 714.48 | No. | 2 | 0 | 1050
4.9 | Remove existing failed lintels and provide and install new 150-250mm x 200mm oak lintels, 1.6m long. (Failed steel lintel on west elevation at 2nd floor to also be removed.) | No | 7 | 920 | 6440 | No | 7 |  | 2731.68 | No | 7 | 0 | 3950
4.10 | Provide new external leaf of masonry, where external stonework is badly weathered and/or missing. Allow for consolidation and/or removal of loose masonry. Construction to be in matching stone with NHL 2.0 lime mortar. External leaf approx. 300mm +/- 100mm | m2 | 20 | 460 | 9200 | m2 | 20 |  | 21424 | m2 | 20 | 0 | 4200
4.11 | Allow for new stone lintel over ground floor NW window | item |  |  | 350 | item |  |  | 549.48 | item |  |  | 850
4.12 | Allow for new stone lintel, reveals and new sill to 1st floor NW window | item |  |  | 350 | item |  |  | 1483.44 | item |  |  | 850
4.13 | Allow for new sill for 1st floor doorway in West elevation | item |  |  | 350 | item |  |  | 604.48 | item |  |  | 1050
4.14 | Allow for new stone lintel over small central window in east elevation | item |  |  | 350 | item |  |  | 549.48 | item |  |  | 660
4.15 | Allow for new stone reveals for 1st floor window in SE corner | item |  |  | 350 | item |  |  | 988.96 | item |  |  | 1130
4.16 | Allow for stitching of 2nd floor external stone lintel over window in SW corner | item |  |  | 220 | item |  |  | 118.12 | item |  |  | 110
4.17 | Clean all stonework internally and externally. Allow for removal of recent painted graffiti | item |  |  | 4000 | item |  |  | 1263.44 | item |  |  | 2075
4.18 | Allow for repointing of walls internally and externally (including external repointing to chimney). Joints to be raked out to twice width of bed joints, and all metal fixings in walls to be removed. Walls to be pointed in NHL 2.0 lime mortar | m2 | 600 | 85 | 51000 | m2 | 600 |  | 34602 | m2 | 600 | 0 | 47400
4.19 | Allow for provision and installation of new Stainless Steel security bars to windows. Stainless steel to be etched and painted black. All existing bars to be removed. Windows approx. 0.9x1.5m | No | 12 | 150 | 1800 | No | 12 |  | 7586.88 | No | 12 | 0 | 14400
4.20 | Allow for provision and installation of new Stainless Steel security bars to doors. Stainless steel to be etched and painted black. All existing bars to be removed. Doors approx. 1.1x2.3m | No | 4 | 150 | 600 | No | 4 |  | 2528.96 | No | 4 | 0 | 5600
4.21 | Allow for provision and installation of new Stainless Steel security bars to arched openings in attached chimney. Stainless steel to be etched and painted black. All existing bars to be removed. Openings approx. 0.7x1.5m | No | 2 | 150 | 300 | No | 2 |  | 1264.48 | No | 2 | 0 | 2200
4.22 | Provide and install 6mm dia. Helifix Stainless steel bed joint reinforcement as crack stitching in engine house | m | 25 | 46 | 1150 | m | 25 |  | 1614 | m | 25 |  | 1125
4.23 | Provide and install 6mm dia. Helifix Stainless steel bed joint reinforcement in attached chimney | m | 20 | 46 | 920 | m | 20 |  | 1291.2 | m | 20 |  | 800
|  |  |  | Sub Total | 110860 |  |  | Sub Total | 131014.52 |  |  | Sub Total | 119060
| Works Total (ALL) |  |  |  | 153300 |  |  |  | 186308.6 |  |  |  | 165335
| Contract Contingency (15%) |  |  |  | 22995 |  |  |  | 27946.29 |  |  |  | 24800.25
| Total |  |  |  | 176295 |  |  |  | 214254.89 |  |  |  | 190135.25

## Breakdown of prof fees
Professional Fees
RIBA Stage 4: Technical Design \ Contract Documents - Incl Free Standing Chimney works | Days | Rate | Total
SI & Design Calculations - Preparation of tender documents (Detailed Specification, Schedule of Works, dwgs, pre-construction information,conditions of contract) | 8 | 550 | 4400
Scheduled Monument Consent Application - Consolidation Works | 2 | 550 | 1100
Planning Consent Application - Consolidation | 2 | 550 | 1100
Tender Queries - Contractor Site Visits | 3 | 550 | 1650
Tender assessment report and award | 2 | 550 | 1100
Project Management / Meetings | 4 | 550 | 2200
11550
RIBA Stage 5: Construction Phase Works (Consolidation Works)
Contract Admin (16 week contract) | 16 | 550 | 8800 | Technical Queries, Site Visits, Contract Management
Pre-Start Meeting | 1 | 550 | 550
Progress Meetings (5) | 5 | 550 | 2750
Monthly Valuations and Payment Certificates | 6 | 550 | 3300
15400
Other costs
Disbursements |  |  | 300
Principal Designer Duties (CDM 2015) Pre-Construction | 4 | 550 | 2200 | Pre-Construction Information
Principal Designer Duties (CDM 2015) Construction Phase | 2 | 550 | 1100 | Review Construction Phase H&S Plan, Prepare H&S File
Archaeological Watching Brief |  |  | 2030
Bat Boxes |  |  | 50
5680
GRAND TOTAL |  |  | 32630

## Interpretation Panels
Interpretation Panels
Nature Sign Design
Steel Signs
Size | Unit Price | Qty | Total
Size A0 | 1025 | 4 | 4100
Design | 300 | 4 | 1200
Delivery | 160 | 1 | 160
Delivery & installation | 795 | 1 | 795
TOTAL ON A0 SIZE |  |  | 6095
Border Signs and Graphics | Unit | Qty | Total
Steel Lectern (707x1000mm) | 780 | 4 | 3120
Steel upright | 865 | 4 | 3460
Design | 160 | 4 | 640
Delivery | 90 | 1 | 90
Installation | 520 | 1 | 520
TOTAL FOR STEEL LECTERN |  |  | 4370
Fitzpatrick Woolmer | Unit | Qty | Total
Musketeer Steel (A0) | 589 | 4 | 2356
Graphics panel | 338 | 4 | 1352
Delivery | 308 | 1 | 308
Site survey | 910 | 1 | 910
Installation | 2880 | 1 | 2880
Design (A0) | 660 | 1 | 660
Design (A0) | 495 | 3 | 1485
Proofs | 40 | 8 | 320
TOTAL WITH INSTALLATION |  |  | 10271
TOTAL WITHOUT INSTALLATION |  |  | 6481
Differentia
Desc. | Unit | Qty | Total
Design & artwork | 550 | 4 | 2200
Copywriting | 250 | 4 | 1000
Lectern & panel | 650 | 4 | 2600
Delivery | 250 | 1 | 250
Installation | 1600 | 1 | 1600
Project management | 800 | 1 | 800
TOTAL |  |  | 8450